## Plan
Plan Chaiyawat (Beer) | [38 empty] | Update Plan 11/30/2020
# | Module | Page | ID From | Description | Status | ต.ค. |  |  |  |  | พ.ย. | [6 empty] | พ.ย. | [6 empty] | พ.ย. | [6 empty] | พ.ย. | [6 empty] | หมายเหตุ
[6 empty] | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  | UI | A0 | UI - Menu | N
1 | Corporate |  |  | Corporate | I
2 | Corporate | analyst |  | วิเคราะห์ระบบ / เอกสารอื่นๆ | F | bar: ต.ค. 27
3 | Corporate | analyst |  | ER Diagram | F | bar: ต.ค. 27
4 | Corporate | analyst |  | Mapping | F | bar: ต.ค. 27
5 | Corporate | analyst |  | Data Flow Diagram | F | bar: ต.ค. 27
6 | Corporate | analyst |  | Design Table / Stored Procedures | F | bar: ต.ค. 27
7 | Corporate | DB | A1 | Table Corporate | F | bar: ต.ค. 27
8 | Corporate | DB | A2 | Table Corporate | F | bar: ต.ค. 27
9 | Corporate | DB | A3 | Table Corporate | F | bar: ต.ค. 27
10 | Corporate | DB | A4 | Table Corporate | F | bar: ต.ค. 27
11 | Corporate | DB | A7 | Table Corporate | F | bar: ต.ค. 27
12 | Corporate | DB | A8 | Table Corporate | F | bar: ต.ค. 27
13 | Corporate | DB | A10 | Table Corporate | F | bar: ต.ค. 27
14 | Corporate | DB | A1 | Table CorporateOwner | F | bar: ต.ค. 27
15 | Corporate | DB | A3 | Table CorporateOwner | F | bar: ต.ค. 27
16 | Corporate | DB | A4 | Table CorporateOwner | F | bar: ต.ค. 27
17 | Corporate | DB | A6 | Table CorporateOwner | F | bar: ต.ค. 27
18 | Corporate | DB | A7 | Table CorporateOwner | F | bar: ต.ค. 27
19 | Corporate | DB | A2 | Table Title | F | bar: ต.ค. 27
20 | Corporate | DB | A2 | Table CorporateImagePart | F | bar: ต.ค. 29
21 | Corporate | DB | A3 | Table CorporateImagePart | F | bar: ต.ค. 29
22 | Corporate | DB | A4 | Table CorporateImagePart | F | bar: ต.ค. 29
23 | Corporate | DB | A7 | Table CorporateImagePart | F | bar: ต.ค. 29
24 | Corporate | DB | A8 | Table CorporateImagePart | F | bar: ต.ค. 29
25 | Corporate | DB | A10 | Table CorporateImagePart | F | bar: ต.ค. 29
26 | Corporate | DB | A2 | Stored Corporate_Create | F | bar: ต.ค. 27
27 | Corporate | DB | A1 | Stored Corporate_LoadList | F | bar: ต.ค. 27
28 | Corporate | DB | A3 | Stored ExecutiveDetailsListLoadCorporateOID | F | bar: ต.ค. 27
29 | Corporate | DB | A4 | Stored ExecutiveDetailsListLoadCorporateOID | F | bar: ต.ค. 27
30 | Corporate | DB | A7 | Stored ExecutiveDetailsListLoadCorporateOID | F | bar: ต.ค. 27
31 | Corporate | DB | A5 | Stored CorporateOwner_Create | F | bar: ต.ค. 27
32 | Corporate | DB | A6 | Stored CorporateOwner_Create | F | bar: ต.ค. 27
33 | Corporate | DB | A15 | Stored CorporateOwner_DeleteByID | F | bar: ต.ค. 27
34 | Corporate | DB | A2 | Stored Title_Create | N
35 | Corporate | DB | A2 | Stored CorporateImagePart_Create | N
36 | Corporate | DB |  | Test Stored | I
37 | Corporate | Class |  | Class | N
38 | Corporate | Class | A1 | LoadCorporateList | N
39 | Corporate | Class | A2 | CreateCorporate | N
40 | Corporate | Class | A3 | LoadCorporateViewList | N
41 | Corporate | Class | A4 | LoadCororateViewTree | N
42 | Corporate | Class | A5 | CorporateAddExecutive | N
43 | Corporate | Class | A6 | CorporateNewExecutive | N
44 | Corporate | Class | A7 | PrintOutCorporate | N
45 | Corporate | UI | A1 | UI - LoadCorporateList | N
46 | Corporate | UI | A2 | UI - CreateCorporate | N
47 | Corporate | UI | A3 | UI - LoadCorporateViewList | N
48 | Corporate | UI | A4 | UI - LoadCororateViewTree | N
49 | Corporate | UI | A5 | UI - CorporateAddExecutive | N
50 | Corporate | UI | A6 | UI - CorporateNewExecutive | N
51 | Corporate | UI | A7 | UI - PrintOutCorporate | N
52 | Executive |  |  | Executive | I
53 | Executive | analyst |  | วิเคราะห์ระบบ / เอกสารอื่นๆ | F | bar: ต.ค. 27
54 | Executive | analyst |  | ER Diagram | F | bar: ต.ค. 27
55 | Executive | analyst |  | Mapping | F | bar: ต.ค. 27
56 | Executive | analyst |  | Data Flow Diagram | F | bar: ต.ค. 27
57 | Executive | DB |  | Design Table / Stored Procedures | F | bar: ต.ค. 27
58 | Executive | DB | A8 | Table Executive | F | bar: ต.ค. 27
59 | Executive | DB | A9 | Table Executive | F | bar: ต.ค. 27
60 | Executive | DB | A10 | Table Executive | F | bar: ต.ค. 27
61 | Executive | DB | A8 | Table CorporateOwner | F | bar: ต.ค. 27
62 | Executive | DB | A10 | Table CorporateOwner | F | bar: ต.ค. 27
63 | Executive | DB | A10 | Table ExecutiveRelation | N
64 | Executive | DB | A11 | Table ExecutiveRelation | N
65 | Executive | DB | A3 | Table ExecutiveImagePart | F | bar: ต.ค. 29
66 | Executive | DB | A4 | Table ExecutiveImagePart | F | bar: ต.ค. 29
67 | Executive | DB | A5 | Table ExecutiveImagePart | F | bar: ต.ค. 29
68 | Executive | DB | A6 | Table ExecutiveImagePart | F | bar: ต.ค. 29
69 | Executive | DB | A8 | Table ExecutiveImagePart | F | bar: ต.ค. 29
70 | Executive | DB | A9 | Table ExecutiveImagePart | F | bar: ต.ค. 29
71 | Executive | DB | A10 | Table ExecutiveImagePart | F | bar: ต.ค. 29
72 | Executive | DB | A9 | Stored Executive_Create | F | bar: ต.ค. 27
73 | Executive | DB | A8 | Stored Executive_LoadList | F | bar: ต.ค. 27
74 | Executive | DB | A10 | Stored RelationDetailsListLoadExecutiveOID | F | bar: ต.ค. 27
75 | Executive | DB | A11 | Stored ExecutiveRelationLoadList | N
76 | Executive | DB | A11 | Stored ExecutiveRelation_Create | N
77 | Executive | DB | A12 | Stored ExecutiveRelation_Create | N
78 | Executive | DB | A9 | Stored ExecutiveImagePart_Create | N
79 | Executive | DB |  | Test Stored | I
80 | Executive | Class |  | Class | N
81 | Executive | Class | A8 | LoadExecutiveList | N
82 | Executive | Class | A9 | CreateExecutive | N
83 | Executive | Class | A12 | CreateExecutive | N
84 | Executive | Class | A10 | LoadExecutiveByID | N
85 | Executive | Class | A11 | ExecutiveAddRelation | N
86 | Executive | Class | A12 | ExecutiveNewRelation | N
87 | Executive | Class | A13 | PrintOutExecutiveRelation | N
88 | Executive | UI | A8 | UI - LoadExecutiveList | N
89 | Executive | UI | A9 | UI - CreateExecutive | N
90 | Executive | UI | A10 | UI - LoadExecutiveByID | N
91 | Executive | UI | A11 | UI - ExecutiveAddRelation | N
92 | Executive | UI | A12 | UI - ExecutiveNewRelation | N
93 | Executive | UI | A13 | UI - PrintOutExecutiveRelation | N
94 | Relation |  |  | Relation | N
95 | Relation | analyst |  | วิเคราะห์ระบบ / เอกสารอื่นๆ | N
96 | Relation | analyst |  | ER Diagram | N
97 | Relation | analyst |  | Mapping | N
98 | Relation | analyst |  | Data Flow Diagram | N
99 | Relation | DB |  | Design Table / Stored Procedures | N
100 | Relation | DB | A14 | Table Relation | N
101 | Relation | DB | A15 | Table Relation | N
102 | Relation | DB | A16 | Table Relation | N
103 | Relation | DB | A17 | Table Relation | N
104 | Relation | DB | A18 | Table Relation | N
105 | Relation | DB | A19 | Table Relation | N
106 | Relation | DB | A14 | Table RelationImagePart | F | bar: ต.ค. 29
107 | Relation | DB | A15 | Table RelationImagePart | F | bar: ต.ค. 29
108 | Relation | DB | A16 | Table RelationImagePart | F | bar: ต.ค. 29
109 | Relation | DB | A16 | Table RelationImagePart | F | bar: ต.ค. 29
110 | Relation | DB | A18 | Table RelationImagePart | F | bar: ต.ค. 29
111 | Relation | DB | A19 | Table RelationImagePart | F | bar: ต.ค. 29
112 | Relation | DB | A14 | Stored Relation_LoadList | N
113 | Relation | DB | A17 | Stored Relation_LoadList | N
114 | Relation | DB | A15 | Stored Relation_Create | N
115 | Relation | DB | A17 | Stored Relation_Create | N
116 | Relation | DB | A18 | Stored Relation_Create | N
117 | Relation | DB | A16 | Stored RelationDetailsListLoadParentByID | N
118 | Relation | DB | A19 | Stored RelationDetailsListLoadParentByID | N
119 | Relation | DB | A15 | Stored RelationImagePart_Create | N
120 | Relation | DB | A18 | Stored RelationImagePart_Create | N
121 | Relation | DB |  | Test Stored | I
122 | Relation | Class |  | Class | N
123 | Relation | Class | A14 | LoadRelationList | N
124 | Relation | Class | A15 | CreateRelation | N
125 | Relation | Class | A16 | LoadRelationListByID | N
126 | Relation | Class | A19 | LoadRelationListByID | N
127 | Relation | Class | A17 | RelationAddParent | N
128 | Relation | Class | A18 | RelationNewParent | N
129 | Relation | Class | A19 | PrintOutRelation | N
130 | Relation | UI | A14 | UI - LoadRelationList | N
131 | Relation | UI | A15 | UI - CreateRelation | N
132 | Relation | UI | A16 | UI - LoadRelationListByID | N
133 | Relation | UI | A17 | UI - RelationAddParent | N
134 | Relation | UI | A18 | UI - RelationNewParent | N
135 | Relation | UI | A19 | UI - PrintOutRelation | N

## WorkLog
Date | Item
2020-02-11 | 123
2020-02-11 | 124

## DBObject
ID | Name | Type
fm_tb_Corporate | fm_tb_Corporate | T
fm_tb_CorporateOwner | fm_tb_CorporateOwner | T
mst_tb_Title | mst_tb_Title | T
fm_tb_Corporate_Image | fm_tb_Corporate_Image | T
fm_tb_Executive | fm_tb_Executive | T
fm_tb_ExecutiveRelation | fm_tb_ExecutiveRelation | T
fm_tb_Executive_Image | fm_tb_Executive_Image | T
fm_tb_Relation | fm_tb_Relation | T
fm_tb_Relation_Image | fm_tb_Relation_Image | T
fm_sp_Corporate_Create | fm_sp_Corporate_Create | T
fm_sp_CorporateLoadList | fm_sp_CorporateLoadList | T
fm_sp_CorporateOwner_Create | fm_sp_CorporateOwner_Create | T
fm_sp_ExecutiveDetailsListLoadCorporateOID | fm_sp_ExecutiveDetailsListLoadCorporateOID | T
fm_sp_Executive_Create | fm_sp_Executive_Create | T
fm_sp_Executive_LoadList | fm_sp_Executive_LoadList | T
fm_sp_RelationDetailsListLoadExecutiveOID | fm_sp_RelationDetailsListLoadExecutiveOID | T
fm_sp_ExecutiveRelation_LoadList | fm_sp_ExecutiveRelation_LoadList | T
fm_sp_ExecutiveRelation_Create | fm_sp_ExecutiveRelation_Create | T
fm_sp_Executive_Image_Create | fm_sp_Executive_Image_Create | T
fm_sp_RelationLoadList | fm_sp_RelationLoadList | T
fm_sp_Relation_Create | fm_sp_Relation_Cretae | T
fm_sp_RelationDetailsListLoadParentOID | fm_sp_RelationDetailsListLoadParentOID | T
fm_sp_Relation_Image_Create | fm_sp_Relation_Image_Create | T
fm_vw_Corporate_LoadList | fm_vw_Corporate_LoadList | V
fm_vw_Executive_LoadList | fm_vw_Executive_LoadList | V
fm_vw_Relation_LoadList | fm_vw_Relation_LoadList | V